## day1
No | Service name | Description | Page(s) | Status | Developer | remark
1 | ageCalculation | Calculate age based on DOB | Quote | Tested | Santi | day1 | Tested
2 | quoteCalculation | Calculate quote based on gender,age,occupation, APE,sum insured | Quote | Tested | Santi | day1 | Coded
3 | sendEmailQuote | Send email to customer | Quote result, Summary page | In progress | Santi | day1 | In progress
4 | sendEmailEReceipt | Attach eReceipt to email to customer | Payment Summary Page | In progress | Tom | day1 | To start
5 | saveApp | Save application data to DB | Application Page | Coded | Santi | day1
6 | getApp | Retrieve application data when customer resume to application page | Application Page | Coded | Santi | day1
7 | lineInfo | Retrieve data from Line BC to display in application page | Application Page | Coded | Santi | day1
8 | getEReciept | Populate data into eReceipt (CBR) | Summary Page | In progress | Tom | day1
9 | getSummary | Populate data into summary page | Application Summary Page | Coded | Santi | day1
10 | getPolicyNumber | Retrieve PNO from DB and populate into eReceipt (CBR) | Summary Page | Coded | Tom | day1
11 | linePay | Integrate to Line Pay to pass payment | Payment page | To start | TBD | day1
12 | uploadDocument | Upload document to shared location | Upload ID Page | To start | TBD | day1
13 | getProvinces | Display Province in dropdown | Application Page | Coded | Tom | day1
14 | getDistricts | Display District in dropdown | Application Page | Coded | Tom | day1
15 | getSubDistricts | Display Sub-district in dropdown | Application Page | Coded | Tom | day1
16 | getNationalities | Display Nationalities in dropdown | Application Page | Coded | Tom | day1
17 | getOccupations | Display occupation in dropdown | Application Page | Coded | Tom | day1
18 | getTaxes | Display Taxes in dropdown | Application Page | Coded | Tom | day1
19 | getMaritalStatus | Display Maritalstatus in dropdown | Application Page | Coded | Tom | day1
20 | getTitles | Display Titles in dropdown | Application Page | Coded | Tom | day1
21 | getRelation | Display province in dropdown | Beneficiary Page | Coded | Santi | day1
22 | OCR | Extract national ID from photo and compare the ID entered in application | Upload ID Page | To start | Dean/Cedric | day1
23 | Convert to PDF | Convert application form to PDF format | Summary Page | In progress | Tom | day1
23 | Convert to PDF | Convert eReceipt to PDF format (internal operations use) | Summary Page | In progress | Tom | day1
24 | Watermark | Print watermark on ID and save into shared location | Upload ID Page | To start | Dean/Cedric | day1
25 | Graph | Populate benefit data into Graph | Quote result | To start | Yalamber | day1
26 | getQuote | Get Header information | Every Page | Coded | Santi | day1
27 | Get Agent Code | Get agent code for existing customer | Summary Page | To start | Tom | day1.x
28 | SendApp | Send application data to TeleInfo | Summary Page | To start | TBD | day1.x